## 0. Read Me
ME Primary Board - Phase 1 Implementation Estimates
Module-by-module effort for the Primary Board. Rev 1.3, 2026-09-01. Code state as of 2026-08-26.
What this workbook is
Every Primary Board module of Phase 1 that still has to be built, what it covers in plain English, how much of it already exists, and what it will cost in engineer-days. This workbook covers the Primary Board only. Phase 2 work, the Battery Manager web application, Secondary Board firmware, M7 firmware and hardware bring-up are all outside these totals - see the exclusions at the foot of this sheet.
The bottom line
| Track | Modules | Build days | Board-test days | Total days | Total hours | Months at 21 days
| Primary Board (1 engineer) | 27 | 113.25 | 62.25 | 175.5 | 1404 | 8.4
| Calendar time | 175.5 days ~ 8.4 months, one engineer working serially.
| Start and finish | Wed 02 Sep 2026 to Wed 05 May 2027, working Monday to Friday.
The thing to act on
Only 3 of the 27 modules can be started today - 11.25 days out of 175.5. Every other module is waiting on a question nobody has answered yet: what 'safe state' means, what the control-loop rate is, how the Modbus register map is laid out for 64 channels, and so on. Those modules still carry their full estimate, because being blocked stops the work starting, it does not make it smaller. Answering the open questions is therefore the highest-value thing anyone can do for this schedule - it does not remove days, but it is what lets the days be spent. The questions are listed with owners in Requirements/Code_Tracebility/ME_Open_Issues_and_TBD_Register.md.
How to read a row
| Build days | Writing the module with Claude Code: the design note, the tests, the code, and both builds passing. Unit tests are included in this number, not added on top of it.
| Board-test days | Proving the module on the real i.MX8M Plus board with a real Secondary Board attached. This is the number that AI does not shrink, because it needs hardware, one engineer and one board at a time.
| Total hours | The same effort expressed in hours. The hours do not change; the day columns are simply those hours divided by an 8-hour working day.
| Start and Finish | When the module is worked on, assuming it is picked up in the order listed and that work runs Monday to Friday from 02 Sep 2026. There is one engineer, so the modules run one after another - a module can begin on the date the previous one ends, because the estimates land on quarter-days and that last day is genuinely shared.
| Already built | How many of the module's requirements the current code already meets in full or in part. A high number means the module is finishing work, not starting it.
| Priority | P1 is needed for a working Phase 1 system. P2 matters for production use. P3 is a third-party interface that no ME board needs in order to run a test.
| Start now? | 'Ready' means the specification is complete enough to begin. 'Waiting' means an open question has to be answered first - the next column names it.
| Waiting on | The open issue (OI-nn) or to-be-decided item (TBD-nn) that gates the module. The full register is in Requirements/Code_Tracebility/ME_Open_Issues_and_TBD_Register.md.
What one day means
One engineer-day here is 8 productive hours, working with Claude Code the way this project has worked since August 2026: test first, a written design note for every real decision, and both builds green before anything is called done. These are already AI-assisted figures, so do not discount them a second time for AI. They are calibrated against measured output, not guessed: 16 sessions between 6 and 21 August 2026 delivered roughly 7,500 lines of source, 4,600 lines of tests and 39 design decisions across about 13 work packages. Modules are priced against that, then loaded for the two things that were not true of those sessions: hardware that does not exist yet, and specifications that have not been written yet.
What is fixed is the HOURS of work, shown in the 'Total hours' column above - 1,404 hours for the Primary Board. Days are a presentation of those hours, so the day length changes the day count and nothing else. The underlying estimate was recorded against a 6-hour day in Code_Tracebility/ME_Work_Packages_and_Estimates.md, which is why that document shows 234 days where this one shows 175.5: the same work, divided by a longer day. Neither figure is a correction of the other.
Four things to know before quoting a date
| 1 | One engineer. Nothing in this plan can be split across people, so the days add directly into calendar days.
| 2 | The dates count weekends as the only non-working days. Public holidays, leave and sick days are not modelled and will push every date after them to the right. Subtract your own holiday calendar before committing to a finish date.
| 3 | A blocked module still costs its full estimate, and the dates assume its open question is answered before its start date arrives. Most modules on this sheet are waiting on one. Every question answered late moves its module, and everything after it, by however long the answer took.
| 4 | Board-test days will not come down. Hardware-in-the-loop testing needs the board, a real Secondary, an M7 build and a running Battery Manager on the same network. A passing build on the PC proves nothing about the target.
Excluded from these totals
| Battery Manager web application | A separate Phase 1 track with its own engineer, and not counted here. It is about 95 more days at the same day length. Its packages are listed in Code_Tracebility/ME_Work_Packages_and_Estimates.md. Several of them cannot finish ahead of the Primary module they pair with, so do not read this sheet as the whole of Phase 1.
| Secondary Board firmware, M7 firmware, mechanical and electrical bring-up | Outside the scope of this software plan entirely.
Generated from Requirements/ME_Phase1_Estimates/tools/build_phase1_estimates.py. Effort and blockers are read from Code_Tracebility/tools/trace_packages.py; build state is read from trace_status.py. Do not hand-edit this workbook - it is overwritten on every build.

## 1. Primary Board Modules
Primary Board Modules
27 modules, one engineer, 175.5 days at 8 hours a day. Build days include unit tests; board-test days are hardware-in-the-loop on the i.MX8M Plus.
# | Module | What it covers | SRS section | Reqs | Already built | Build days | Board-test days | Total days | Total hours | Start | Finish | Priority | Start now? | Waiting on | Work packages
M01 | Secondary Board enrolment | The Primary asks the internal CAN bus which Secondary Boards are present and how many channels each one has, instead of being told on the command line. This is the largest gap between the code as built and the SRS, and several other modules wait behind it. | 13.0 | 11 | 2 | 4.5 | 2.25 | 6.75 | 54 | 2026-09-02 | 2026-09-10 | P1 | Waiting | OI-26, OI-25, TBD-19 | WP-P01
M02 | Scale-out to 64 channels | Run the real target size: 8 Secondary Boards x 8 channels. The addressing and the 64 storage slots are already written and tested on the PC. What has never run is more than one Secondary Board or more than 4 channels on real hardware. | 12.0 | 10 | 8 | 3.75 | 3 | 6.75 | 54 | 2026-09-10 | 2026-09-21 | P1 | Waiting | TBD-18 / OI-24 (is the address range 8x8 or 15x15) | WP-P27
M03 | Program operators | The remaining test-program commands: Pause, Discharge, Interrupt, loops, jumps, register, error, message and table steps. Three of the thirteen are built, and this is the largest functional module in Phase 1. | 10.0 | 58 | 5 | 9 | 3.75 | 12.75 | 102 | 2026-09-21 | 2026-10-08 | P1 | Waiting | OI-16 (REG), OI-17 (SET), OI-20 (DCH/INT/ERR/MSG), OI-22 (cycle nesting) | WP-P02
M04 | Charge / discharge control modes | Constant-voltage mode, the constant-current to constant-voltage hand-over, non-time step limits, and the clamp that stops a program asking for more current than the channel is configured to allow. Today only plain constant-current charging with a time limit works. | 10.0, 8.0 | 8 | 2 | 4.5 | 3 | 7.5 | 60 | 2026-10-08 | 2026-10-19 | P1 | Waiting | OI-20, and REQ_198 needs a temperature source binding | WP-P03
M05 | Cut-off condition engine | The rules that end a step: 13 condition types, 6 comparators, several conditions on one step, and debounce so that a single noisy sample cannot end a test. One condition type and two comparators are built today. | 24.0 | 7 | 4 | 3.75 | 1.5 | 5.25 | 42 | 2026-10-19 | 2026-10-26 | P1 | Waiting | TBD-36 (how many per step), TBD-37 (debounce count) | WP-P04
M06 | Test records | Produce the stored test result and send it to the Battery Manager on UDP 10001. The delivery path is already built end to end and is carrying nothing; the data it needs is decoded today and then thrown away. | 16.0 | 4 | 1 | 3 | 1.5 | 4.5 | 36 | 2026-10-27 | 2026-11-02 | P1 | Waiting | TBD-26 (registration types and interval range) | WP-P05
M07 | Live data completeness | Fill the fields in the live once-per-second data packet that are still sent as zero: temperature, power, the capacity and energy totals, and the cycle counters. The packet layout itself is finished and verified on hardware. | 16.0, 15.0 | 4 | 4 | 2.25 | 0.75 | 3 | 24 | 2026-11-02 | 2026-11-05 | P2 | Ready | - | WP-P06
M08 | Host link hardening | Make the replies to the Battery Manager honest: say 'accepted' where the board today says 'done', refuse a command it does not recognise instead of acknowledging it, cap the number of sessions, and hold data while the link is down. Most of this section already works and is hardware-verified. | 15.0 | 17 | 12 | 3.75 | 1.5 | 5.25 | 42 | 2026-11-05 | 2026-11-12 | P1 | Waiting | TBD-12 (session count), TBD-13 (buffering duration), OI-08 | WP-P23
M09 | Test control commands | Finish Pause, Continue, Reset and the group (all-channel) operations, and check the preconditions before a Start. All six commands are accepted and acknowledged today, but only Start and Stop actually do anything. | 17.0 | 9 | 2 | 3.75 | 2.25 | 6 | 48 | 2026-11-12 | 2026-11-20 | P1 | Waiting | OI-05 (safe state), TBD-27/OI-30 (Start on a completed test), OI-29 (command scoping) | WP-P22
M10 | Fault handling and error codes | One error catalogue - code, severity, subsystem, channel, time - and a fault model that knows whether a fault affects one channel, one board or the whole system, plus detection of a stalled control thread. Per-channel isolation already works; the classification around it does not exist. | 18.0, 21.0 | 8 | 2 | 7.5 | 3.75 | 11.25 | 90 | 2026-11-20 | 2026-12-07 | P1 | Waiting | OI-05 (safe state), OI-11 (error catalogue) | WP-P10, WP-P11, WP-P31
M11 | Internal CAN bus robustness | Recover from bus-off, notice stale readings, set message priorities, count errors and stay inside a bus-load budget. The transport itself works and is partly hardware-verified; this is what keeps it working on a bad day. It also needs a matching change on the M7 core, which owns the CAN controller. | 14.0 | 10 | 5 | 3.75 | 2.25 | 6 | 48 | 2026-12-08 | 2026-12-15 | P1 | Waiting | TBD-20, TBD-21 (bit rates), TBD-22 (load budget), TBD-24 (staleness), OI-27 | WP-P25
M12 | Analog limits per channel | Store and validate each channel's maximum battery voltage, its maximum charge and discharge currents and its sampling rates, then act on the six named exceptions. Nothing is stored today, which is why the current clamp in M04 has nothing to clamp against. | 8.0 | 24 | 0 | 3.75 | 2.25 | 6 | 48 | 2026-12-16 | 2026-12-23 | P1 | Waiting | TBD-15 ('near 0 V' threshold) | WP-P19
M13 | Performance and timing budgets | Prove that the control loop holds its interval for 64 channels, that jitter stays inside its limit with headroom to spare, and that memory use is within budget. This is mostly measurement on real hardware, which is why board time exceeds build time. The control-loop rate is the single most important open number in the SRS. | 19.0 | 8 | 3 | 3 | 3.75 | 6.75 | 54 | 2026-12-24 | 2027-01-01 | P1 | Waiting | TBD-28 (control interval), TBD-29, TBD-30, TBD-31, TBD-32, OI-03, OI-31 | WP-P26
M14 | Real Time Clock | The I2C clock chip, time stamps in both required formats, time sync from the host, and pushing time out to the Secondary Boards. A time correction must not create a jump in a running test's elapsed time. Hardware-critical: needs the datasheet and a board. | 4.0 | 8 | 2 | 3 | 2.25 | 5.25 | 42 | 2027-01-01 | 2027-01-08 | P1 | Waiting | TBD-04 (permitted Primary-to-Secondary offset) | WP-P13
M15 | Startup, shutdown and persistence | Do not accept commands before the board is ready, bring every channel to a safe state on shutdown, keep configuration, calibration and programs across a restart, and report software versions. Everything is in RAM today, so a restart loses every program and every setting. | 20.0 | 9 | 1 | 7.5 | 3.75 | 11.25 | 90 | 2027-01-11 | 2027-01-26 | P1 | Waiting | TBD-33 (time to ready), OI-05 (safe state), OI-15 (medium, on-media format, partial-write handling) | WP-P09, WP-P07, WP-P30
M16 | Power-fail detection and resume | Detect the supply failing, save enough state to resume, and pick the test back up on restart. Waiting on a hardware number, not on software: nobody has yet stated how much warning the board's power circuit gives. | 23.0 | 6 | 0 | 3.75 | 2.25 | 6 | 48 | 2027-01-26 | 2027-02-03 | P2 | Waiting | TBD-35 (guaranteed warning time - HARDWARE), OI-15, OI-34 (safety of automatic resume) | WP-P08
M17 | Program management | Verify that a downloaded program is intact, refuse a download to a channel that is running, read a program back, and enforce the storage limit. The step-chain checks are already there; the whole-program checks are not. | 11.0 | 9 | 3 | 3 | 1.5 | 4.5 | 36 | 2027-02-03 | 2027-02-09 | P2 | Waiting | TBD-17 (maximum program size per channel), OI-23 | WP-P21
M18 | Diagnostics and logging | A log that survives a restart and can be retrieved and filtered by channel, board, severity and time. Today logging goes to the console and is gone when the process stops. | 21.0 | 5 | 1 | 3 | 0.75 | 3.75 | 30 | 2027-02-09 | 2027-02-15 | P2 | Waiting | TBD-34 (retention) | WP-P12
M19 | Calibration | Voltage, current and analog-output calibration per channel, stored and tied to the identity of the board it was measured on. There is nothing to carry forward from the old system and no written procedure yet. Wrong constants after a board swap produce readings that look completely believable. | 8.0, 9.0 | 6 | 0 | 4.5 | 3 | 7.5 | 60 | 2027-02-15 | 2027-02-24 | P2 | Waiting | TBD-16 and OI-13 (there is no procedure to implement), OI-14 (board binding) | WP-P20
M20 | Digital inputs | The 4 Primary digital inputs: detect edges, time-stamp them, allow them to be enabled or disabled, and read the Secondary Boards' inputs through the Primary. No digital-input code exists at all. Hardware-critical (GPIO). | 1.0 | 9 | 0 | 2.25 | 1.5 | 3.75 | 30 | 2027-02-25 | 2027-03-02 | P2 | Waiting | TBD-01 (time-stamp resolution) | WP-P14
M21 | Digital outputs | The 4 Primary digital outputs: command a level, enable or disable an output, and drive it to a safe state if the link drops or a fault occurs. Hardware-critical (GPIO), and the safe-state half is safety-relevant. | 2.0 | 10 | 0 | 2.25 | 1.5 | 3.75 | 30 | 2027-03-02 | 2027-03-08 | P2 | Waiting | TBD-02 (safe-state time), OI-05 (what 'safe' is) | WP-P15
M22 | Charge / discharge change-over | Record the bank type of each channel and enforce the dead time when swinging between charge and discharge. It is small in code and safety-relevant, and its size depends entirely on whether the Primary or the Secondary sequences the change-over. | 3.0 | 2 | 0 | 1.5 | 1.5 | 3 | 24 | 2027-03-08 | 2027-03-11 | P2 | Waiting | TBD-03 (dead time), OI-06 (who sequences it) | WP-P28
M23 | Network configuration | Set a static IP or turn DHCP on and off from the Battery Manager, read the MAC address back on demand, and finish the remaining registration queries. The MAC is already read from the real interface and reported at registration. | 6.0 | 7 | 3 | 3 | 1.5 | 4.5 | 36 | 2027-03-11 | 2027-03-17 | P3 | Ready | - | WP-P24
M24 | Configurable CAN ports | User-defined CAN ports towards third-party equipment: configure ports, messages and signals, subscribe, publish and map to output. That is 69 requirements in all, the largest single block in the SRS, and it cannot reuse the existing internal-bus CAN code. | 7.0 | 71 | 0 | 11.25 | 4.5 | 15.75 | 126 | 2027-03-18 | 2027-04-08 | P3 | Waiting | TBD-14 (which port), OI-09 (physically distinct?), OI-10 (11-bit, 29-bit or both) | WP-P18
M25 | RS-485 and Modbus | Port 1 answers a third-party HMI as a Modbus slave; port 2 reads third-party instruments as a Modbus master and binds what it reads to a channel so a program can use it. No RS-485 or Modbus code exists, and the register map for 64 channels has not been agreed. | 5.0 | 16 | 0 | 9 | 4.5 | 13.5 | 108 | 2027-04-08 | 2027-04-28 | P3 | Waiting | TBD-05 (register map for 64 channels), OI-07, TBD-06, TBD-07, TBD-08, TBD-09, TBD-10, TBD-11 | WP-P16, WP-P17
M26 | Analog output as engineering values | Command the analog output in volts and amps rather than raw converter codes. Already true for current; the voltage half is what is left, and it folds naturally into M04. | 9.0 | 1 | 1 | 0.75 | 0.75 | 1.5 | 12 | 2027-04-28 | 2027-04-29 | P3 | Waiting | T-66 (should CCChg ever carry a non-zero voltage) | WP-P29
M27 | Known code items to close out | The small defects and audits the team has already written down against the existing code: the frame-length table audit, a premature acknowledgement, payload-length guards. This is real work with no requirement of its own, listed here so that it is not forgotten. | - | - | - | 2.25 | 1.5 | 3.75 | 30 | 2027-04-29 | 2027-05-05 | P1 | Ready | - | WP-P32
| TOTAL | 27 modules |  | 337 | 61 | 113.25 | 62.25 | 175.5 | 1404 | 2026-09-02 | 2027-05-05
Reading order. Modules are listed in the order the work should be done, not by SRS number: what unblocks other modules comes first, and the independent third-party interfaces come last.
Ready to start today. 3 of 27 modules, worth 11.25 of the 175.5 days on this sheet. Every other module needs an open question answered first - the 'Waiting on' column names it. Those modules are not cheaper for being blocked; they simply cannot be started.
About the dates. One engineer, so modules run one after another in the order listed, Monday to Friday from 02 Sep 2026. A module can begin on the date the previous one ends because the estimates land on quarter-days and that day is genuinely shared. Weekends are the only non-working days modelled - public holidays and leave are not, and will move every later date to the right.
About the 'Reqs' column. It counts the requirements this module's work packages own, which is very close to - but not always exactly - the count of its SRS section, because a few requirements are implemented by a module other than the one their section number suggests. M27 owns no requirement of its own: it is code debt the team has already written down.