## Bug Detail
Sr No | Category | Customer Issue / Observation | ADPL (Our) Action / SI Remark | Customer Remark (ADPL Remark) | Latest Status | Resolved In / Fix Version | Still Open?
── General ──
V0.1-1 | General | Provide detailed software installation procedure including DB config, backup & restore steps. |  |  | Fixed |  | ✓ No
── GUI ──
V0.1-2 | GUI | Offline circuits should display in white color with 'OFFLINE' status on GUI. | Done ¦ Fixed in BTS_BETA_V0.4 | Issue resolved — offline shown when no SW-Primary communication. | Fixed | V0.4 (21-Jan-2026) | ✓ No
V0.1-3 | GUI | Double-click circuit box: show running program, highlight running step, live registration with default graphics (like BM4). | Fixed in BTS_BETA_V0.5 | Running step not yet highlighted in Apr release. | Partial | V0.5 (05-Mar-2026) | ✓ No
V0.1-4 | GUI | Multi-circuit selection via Ctrl/drag; apply Start/Stop/Interrupt to multiple circuits at once. | On-click multi-circuit selection & command execution supported. |  | Fixed | V0.1 onwards | ✓ No
V0.1-5 | GUI | Add 'Reset' option in left-click toolbar on circuit box (like BM4). |  |  | Fixed |  | ✓ No
── Program Control ──
V0.1-6 | Program Control | During running program: allow skip/change steps, log user changes in comment line; changes must not affect saved program (like BM4). |  |  | Open |  | ⚠ YES
── Data Log ──
V0.1-7 | Data Log | If program stopped by BTS or after program time, indicate in registration data (like BM4). |  |  | Fixed |  | ✓ No
── Program Control ──
V0.1-8 | Program Control | 50A charging program continues beyond set 1-minute time — termination inconsistency. |  | Issue resolved (FEB-13 onwards). | Fixed | ~Feb 2026 | ✓ No
── Data Log ──
V0.1-9 | Data Log | Time difference between data file time and actual PC time — inconsistency in battery sessions. | Corrected | Issue resolved. | Fixed | Dec-12 file | ✓ No
── Program Control ──
V0.1-10 | Program Control | In running program: give Interrupt then Continue — circuits do not resume. | Fixed in BTS_BETA_V0.5 | Issue resolved (Mar-16). | Fixed | V0.5 (05-Mar-2026) | ✓ No
── System ──
V0.1-11 | System | PC sleep mode: after wake, system doesn't work; need software/board restart. | Server must not enter sleep mode — connections lost on sleep. |  | Info Only | N/A (server policy) | ✓ No
── Error Handling ──
V0.1-12 | Error Handling | Error codes and error messages per specifications. |  |  | Fixed |  | ✓ No
── Data Export ──
V0.1-13 | Data Export | Export / create new database for sharing with customer (refer BM4 manual pg 71). |  |  | Fixed |  | ✓ No
── GUI ──
V0.1-14 | GUI | Externally stopped circuits should update operator status to 'Stop' (not last running step). |  | Issue resolved (Mar-16). | Fixed | ~Mar 2026 | ✓ No
── Data Export ──
V0.1-15 | Data Export | Data file export — refer attached email for format details. |  |  | Fixed |  | ✓ No
── Data Log ──
V0.1-16 | Data Log | Data file name should use unique identification: circuit+time+date+battery. | Current format: UTCTimeTick_DeviceId_CircuitId |  | Fixed | Dec-12 file | ✓ No
V0.1-17 | Data Log | If no communication, data logs not saved. | Logging depends on active/stable PC connection. |  | Info Only | N/A (design note) | ✓ No
── Program Control ──
V0.1-18 | Program Control | Program does not execute as per set value for 'greater than' condition. | Resolved ¦ Fixed in BTS_BETA_V0.4 | Issue resolved in V0.4. | Fixed | V0.4 (21-Jan-2026) | ✓ No
V0.1-19 | Program Control | If program running on circuit, SW should not allow downloading new program. | Resolved | Issue resolved; shows 'Failed' status if attempted. | Fixed | Dec-12 / V0.4 | ✓ No
── HW/SW Interface ──
V0.1-20 | HW/SW Interface | CHA→DCH step change takes 23ms; spec requires ≤10ms. | Issue of secondary controller. | In process (Mar-16 / Apr-02). | Partial | Secondary Board Fix Pending | ✓ No
── Program Editor ──
V0.1-PE-a | Program Editor | Insert new steps via right-click on program line. | Fixed in BTS_BETA_V0.5 | Done (Mar-16). | Fixed | V0.5 (05-Mar-2026) | ✓ No
V0.1-PE-b | Program Editor | Copy existing steps via right-click. | Fixed in BTS_BETA_V0.5 | Done. | Fixed | V0.5 (05-Mar-2026) | ✓ No
V0.1-PE-c | Program Editor | Delete steps via right-click. | Fixed in BTS_BETA_V0.5 | Done. | Fixed | V0.5 (05-Mar-2026) | ✓ No
V0.1-PE-d | Program Editor | Add/edit comment lines via right-click. | Fixed in BTS_BETA_V0.5 | Done. | Fixed | V0.5 (05-Mar-2026) | ✓ No
V0.1-PE-e | Program Editor | Save program / Save As to create similar programs. | Fixed in BTS_BETA_V0.5 | Not resolved (Apr-02); Save As still pending. | Partial | V0.5 | ✓ No
V0.1-PE-f | Program Editor | OK to confirm / Cancel to discard changes. | Added | Done. | Fixed | Dec-12 file | ✓ No
V0.1-PE-g | Program Editor | Rename the program. | Added | Done. | Fixed | Dec-12 file | ✓ No
── Operators ──
V0.1-OP-a | Operators | Replace 'Pause' wording with 'Interrupt'. | Done | Still shows 'Pause' on status — pending text fix. | Partial | V0.5 shows Interrupt on interrupt action, label fix pending | ✓ No
V0.1-OP-b | Operators | SET, CYCLE, TASK, Table, Interrupt operators — per BM4 manual. | SET Variable done in V0.4; others partial. | Cycle, INT function still pending (Jan-30 / later files). | Partial | V0.4/V0.5 Partial | ✓ No
V0.1-OP-c | Operators | INT operator: no nominal value needed when creating program. | Resolved | Resolved. | Fixed | Dec-12 / V0.4 | ✓ No
V0.1-OP-d | Operators | ERR MSG REG operator — need clear usage explanation (per BM4). | Fixed in BTS_BETA_V0.5 (REG still in progress) |  | Partial | V0.5 | ✓ No
V0.1-OP-e | Operators | Power operator function not working. |  | Power operator working (Jan-30 onwards). | Fixed | ~Jan 2026 | ✓ No
V0.1-OP-f | Operators | Ramp function and Resistance function (BM4 pg 193). |  |  | Open |  | ⚠ YES
V0.1-OP-g | Operators | Parallel and Task operator function not implemented (BM4 pg 193, 229). |  |  | Open |  | ⚠ YES
V0.1-OP-h | Operators | INT operator function not implemented. | Fixed in BTS_BETA_V0.5 |  | Fixed | V0.5 (05-Mar-2026) | ✓ No
── Cut-off Condition ──
V0.1-CO-a | Cut-off Condition | Cut-off 'Equal To' does not execute properly — process exceeds set limit. | Resolved ¦ Fixed in BTS_BETA_V0.4 | Resolved in V0.4. | Fixed | V0.4 (21-Jan-2026) | ✓ No
V0.1-CO-b | Cut-off Condition | AhAcc and WhAcc to be included as cut-off conditions. | Added | Resolved — added in cutoff condition. | Fixed | Dec-12 / V0.4 | ✓ No
V0.1-CO-c | Cut-off Condition | PercAh function not implemented (BM4 pg 197). |  |  | Open |  | ⚠ YES
V0.1-CO-d | Cut-off Condition | Cut-off for current & voltage (> and <) not executing as expected. | Resolved ¦ Fixed in BTS_BETA_V0.4 | Resolved in V0.4. | Fixed | V0.4 (21-Jan-2026) | ✓ No
V0.1-CO-e | Cut-off Condition | Cut-off condition for WH — yet to be done (BM4). | Added | Resolved in V0.4. | Fixed | V0.4 | ✓ No
V0.1-CO-f | Cut-off Condition | Cut-off condition for Power — yet to be done (BM4). | Added | Resolved in V0.4. | Fixed | V0.4 | ✓ No
── Registration ──
V0.1-RC-a | Registration | Registration for WH set value — yet to be done. | Added | Resolved in V0.4. | Fixed | V0.4 | ✓ No
V0.1-RC-b | Registration | Data registration time is 100ms; spec requires 10ms. |  | Resolved in V0.4. | Fixed | V0.4 | ✓ No
── Data Log ──
V0.1-LD-a | Data Log | Last line of data (STOP line) missing in registration. | Fixed in BTS_BETA_V0.5 | Not resolved in Apr-02 — stop line missing. | Partial | V0.5 partial — still open | ✓ No
V0.1-LD-b | Data Log | Data file: include operator name (not number) and cycle information. | Operator Added; Cycle pending. | Cycle information still pending. | Partial | V0.5 — Cycle pending | ✓ No
V0.1-LD-c | Data Log | Double-clicking data file should open it. | Added ¦ In Process | Not resolved (Apr-02). | Fixed |  | ✓ No
V0.1-LD-d | Data Log | View: step AH, Charge AH, Discharge AH, cumulative AH, Cycle, Cycle level (like BM4). | Cycle and Cycle level pending. | Still pending. | Partial | Pending | ✓ No
── GUI ──
V0.3-1 | GUI | Display should show STOP status. | Fixed in BTS_BETA_V0.4 | Resolved (Mar-16). | Fixed | V0.4 (21-Jan-2026) | ✓ No
V0.3-2 | GUI | Selection options required for parameters on display. | Fixed in BTS_BETA_V0.4 | Resolved. | Fixed | V0.4 | ✓ No
V0.3-3 | GUI | Add Cycle, Wh Accu, and Program Name to display parameters. | Fixed in BTS_BETA_V0.4 | Cycle & WhAcc added; Program Name added (Mar-16). | Fixed | V0.4 | ✓ No
── Cut-off Condition ──
V0.3-4 | Cut-off Condition | Cutoff condition with 'equal to' comparator not working. | Fixed in BTS_BETA_V0.4 | Resolved. | Fixed | V0.4 | ✓ No
── Registration ──
V0.3-5 | Registration | Registration data: include step time and cycle. | In progress | Still in progress (Mar-16). | Partial | In Progress | ✓ No
── Data Log ──
V0.3-6 | Data Log | Remove current/voltage symbols and Error/Status columns from registration data. | Fixed in BTS_BETA_V0.4 | Done (Mar-16). | Fixed | V0.4 | ✓ No
── Data Export ──
V0.3-7 | Data Export | Export data file: not all parameters needed in GUI — add to exported file. | Export file in progress | Still in progress. | Partial | In Progress | ✓ No
── GUI ──
V0.3-8 | GUI | GUI parameters: Step Time, Prog Time, Step, Operator, Cycle, Voltage, Current, Ah Acc, Wh Acc, Message. | Fixed in BTS_BETA_V0.5 | Resolved (Mar-16). | Fixed | V0.5 (05-Mar-2026) | ✓ No
── Program Control ──
V0.3-9 | Program Control | Cyclic program: 2 cycles set, only 1 completed. | Fixed in BTS_BETA_V0.4 | Cycle counter resets after completion — not showing completed cycles (Apr-02). | Partial | V0.4 partial | ✓ No
V0.3-10 | Program Control | Cyclic program: 10 cycles configured, 8 completed — 2 missed. | Fixed in BTS_BETA_V0.4 | Same counter reset issue (Apr-02). | Partial | V0.4 partial | ✓ No
V0.3-11 | Program Control | Goto function does not work. | Fixed in BTS_BETA_V0.4 | Goto works (Mar-16). | Fixed | V0.4 | ✓ No
── Cut-off Condition ──
V0.3-12 | Cut-off Condition | Cutoff condition with 'less than' comparator not working. | Fixed in BTS_BETA_V0.4 | Resolved. | Fixed | V0.4 | ✓ No
── Program Editor ──
V0.3-13 | Program Editor | Add/Copy/Delete via right-click (not at column end). | Fixed in BTS_BETA_V0.5 | Resolved (Mar-16). | Fixed | V0.5 (05-Mar-2026) | ✓ No
── System ──
V0.3-14 | System | Exception error while saving battery and program. | Fixed in BTS_BETA_V0.4 | Resolved. | Fixed | V0.4 | ✓ No
── GUI ──
V0.3-15 | GUI | GUI should show offline status when SW-Primary board comm is lost. | Fixed in BTS_BETA_V0.4 | Shows offline correctly (Mar-16). | Fixed | V0.4 | ✓ No
V0.3-16 | GUI | Add proper naming for each tab under Battery Action and Circuits. | Fixed in BTS_BETA_V0.4 |  | Fixed | V0.4 | ✓ No
── System ──
V0.4-17 | System | On power-up: retrieve circuit details (running program, status, Ah, Wh). | Need to discuss with ADPL team. | Need last run program name; power-fail state recovery required (Mar-16). | Partial | Current Deatails are displayed | ✓ No
── Data Log ──
V0.4-19 | Data Log | Step change reading not registered in data file. | Fixed in BTS_BETA_V0.5 | Not resolved (Apr-02). | Partial | V0.5 partial — Apr-02 still open | ⚠ YES
── GUI ──
V0.4-20 | GUI | Interrupt should show 'Interrupt' status, not 'Pause'. | Fixed in BTS_BETA_V0.5 | Resolved (Mar-16). | Fixed | V0.5 (02-Mar-2026) | ✓ No
── System ──
V0.4-21 | System | Power failure during run: circuit should restart from last step after power restore. | Power failure module under development. |  | Open | Under Development | ⚠ YES
── HW/SW Interface ──
V0.4-22 | HW/SW Interface | CCCV function: 'less than' condition for current does not work. | Secondary board bug. | Not resolved (Mar-16 / Apr-02). | Open | Secondary Board Bug | ✓ No
V0.4-23 | HW/SW Interface | DCH CV: after set voltage reached, current does not decrease. | Secondary board bug. | Not resolved (Mar-16 / Apr-02). | Open | Secondary Board Bug | ✓ No
── GUI ──
V0.4-24 | GUI | Graph: flexible X and Y axis selection/scaling (time, cycle, voltage, current, Ah, Wh). | Fixed in BTS_BETA_V0.5 | Scale settings still pending; V/I scale should be on left (Mar-16). | Partial | V0.5 partial | ✓ No
── Program Editor ──
V0.4-25 | Program Editor | Program editor: added action disappears when clicking next line — editor should retain all actions. | Fixed in BTS_BETA_V0.5 | Resolved (Mar-16). | Fixed | V0.5 (05-Mar-2026) | ✓ No
── GUI ──
V0.4-26 | GUI | Registration data window: full-window view, min 60 lines visible. | Fixed in BTS_BETA_V0.5 | Resolved; need font size increase and step time in report (Mar-16). | Partial | V0.5 partial — font/field pending | ✓ No
── Data Log ──
V0.4-27 | Data Log | Data lines missing in 1-hour registration run. | Fixed in BTS_BETA_V0.5 | Resolved (Mar-16). | Fixed | V0.5 (05-Mar-2026) | ✓ No
── Program Editor ──
V0.4-28 | Program Editor | Program editor: user-friendly format (auto-spacing, case, clear layout). | Fixed in BTS_BETA_V0.5 | Resolved (Mar-16). | Fixed | V0.5 (05-Mar-2026) | ✓ No
── GUI ──
V0.4-29 | GUI | IDLE status should show 'Stop', not 'IDLE'. | Fixed in BTS_BETA_V0.5 | Resolved (Mar-16). | Fixed | V0.5 (02-Mar-2026) | ✓ No
── System ──
V0.4-31 | System | After PC restart, circuit shows offline but data still updating — status mismatch. | Will be handled in Error module implementation. |  | Partial |  | ✓ No
── GUI ──
V0.4-32 | GUI | Registration data window should open maximized. | Fixed in BTS_BETA_V0.5 | Resolved (Mar-16). | Fixed | V0.5 (05-Mar-2026) | ✓ No
V0.4-33 | GUI | Chart window: full-screen (maximized) mode. | Already present (Img 1 in Images by APL sheet). | Resolved. | Fixed | V0.5 | ✓ No
── Program Editor ──
V0.4-34 | Program Editor | Program editor window: full-screen mode, clear layout. | Fixed in BTS_BETA_V0.5 | Resolved (Mar-16). | Fixed | V0.5 (05-Mar-2026) | ✓ No
── Data Export ──
V0.4-35 | Data Export | Data file: unique name, double-click to open, right-click menu (Export, Program Details, Go to Record, Delete, Save As). | Need to discuss with ADPL team. |  | Open |  | ✓ No
── Program Control ──
V0.4-36 | Program Control | Goto function works only for next step — random/previous step navigation fails. | We have not seen this; please recreate. | In process (Mar-16). | Partial |  | ✓ No
── Data Export ──
V0.4-37 | Data Export | Print and Page Setup features not implemented. | Export button provided in V0.5. | Resolved (Mar-16). | Fixed | V0.5 (05-Mar-2026) | ✓ No
── GUI ──
V0.4-38 | GUI | Display program name instead of program ID. | Fixed in BTS_BETA_V0.5 | Resolved (Mar-16). | Fixed | V0.5 (02-Mar-2026) | ✓ No
── Data Export ──
V0.4-39 | Data Export | Registration data: view/analyze multiple sessions simultaneously; table+graph; adjust X/Y axis; print. | Fixed in BTS_BETA_V0.5 |  | Fixed | V0.5 (05-Mar-2026) | ✓ No
── GUI ──
V0.4-40 | GUI | Data updating while running but GUI still shows offline. | Will be handled in Error module. |  | Fixed |  | ✓ No
── General ──
V0.4-41 | General | Provide DB architecture info: circuit DB, user DB. | (Deepak) Ok. |  | Info Only | Acknowledged | ✓ No
V0.4-42 | General | Database storage and backup process (BM4 pg 371-372). | (Deepak) Need to discuss with ADPL team. |  | Fixed |  | ✓ No
── GUI ──
V0.4-43 | GUI | Circuit view dialog needed (BM4 pg 123). | (Nikhil) Need to discuss with ADPL team. |  | Fixed |  | ✓ No
── General ──
V0.4-44 | General | Circuit channels, net assign channels (BM4 pg 131-139). | Need to discuss with ADPL team. |  | Fixed |  | ✓ No
── Registration ──
V0.4-45 | Registration | Rlevel registration formats (BM4 pg 186). | Not yet considered for development. |  | Fixed | Not Yet Started | ✓ No
── Program Control ──
V0.4-46 | Program Control | Cell voltage option for nominal value (BM4 pg 193). | Will be covered during CAN implementation. |  | Fixed | CAN Implementation Phase | ✓ No
V0.4-47 | Program Control | PercAh, AhDef.VNC in limit values (BM4 pg 197). | Not yet considered for development. |  | Open | Not Yet Started | ⚠ YES
V0.4-48 | Program Control | Battery parameters in limit values: nominal capacity, cells, charge factor, nominal voltage (BM4 pg 180-181). | Not yet considered for development. |  | Open | Not Yet Started | ⚠ YES
── Data Log ──
V0.4-49 | Data Log | Registration interval 10ms — some records missing. | Fixed in BTS_BETA_V0.5 | In process (Mar-16 / Apr-02). | Partial | V0.5 partial | ✓ No
── Data Log ──
V0.5-99 | Data Log | Cutoff condition executes but not recorded in registration data. |  |  | Fixed |  | ✓ No
── Cut-off Condition ──
V0.5-100 | Cut-off Condition | Cutoff condition not executing at set value — Current < 45A cuts off at ~39A. |  |  | Fixed |  | ✓ No
── Data Log ──
V0.5-104 | Data Log | Registration at 1ms — data loss observed. |  |  | Fixed |  | ✓ No
── GUI ──
V0.5-105 | GUI | Program running time 3 seconds but GUI shows 4 seconds. |  |  | Fixed |  | ✓ No
V0.5-106 | GUI | Report page: switching pages resets view to top instead of keeping position. |  |  | Fixed |  | ✓ No
V0.5-107 | GUI | Program tab: 'Duration (min)' and 'Max Ah' columns unclear — empty, need clarification. |  |  | Info Only |  | ✓ No
V0.5-108 | GUI | Program tab: rename options — Edit→Rename, Duplicate→Save As, Code→Program Edit; add to right-click menu. |  |  | Fixed |  | ✓ No